## Product Backlog
Category | Perspective | Item | Estimated Effort | Priority | Comments | State | Related to Sprint | Related to GitHub Issue(s)
(A) Provide useful information to citizens | Government (Civil Protection) | As Gov. we need to detect places of Swales (المخرات) from concerned authorities. |  | High |  | Upcoming | Sprint 1
|  | As Gov. we need to detect places & times of historical rainstorms from concerned authorities. |  | High |  | Upcoming | Sprint 1
|  | As Gov. we need to get data about rain preceptation from concerned authorities. |  | Medium |  | Upcoming
|  | As Gov. we need to identify the most vulnerable places to rainstorms from concerned authorities. |  | High |  | Upcoming | Sprint 1
|  | As Gov. we need to identify the urban contexts around swales from concerned authorities. |  | Medium |  | Upcoming
|  | As Gov. we need to inform citizens about shelter places. |  | High |  | Upcoming | Sprint 1
|  | As Gov. we need to warn citizens about any expected rainstorms. |  | High |  | Upcoming | Sprint 1
|  | As Gov. we need to setup an evacuation plan in case of rainstorms. |  | Medium |  | Upcoming
(B) Getting useful information from citizens | Volunteer | As a volunteer I want to be able to inform about incidences. |  | High |  | Upcoming | Sprint 1
|  | As a volunteer I need to Register myself to provide services and support. |  | low |  | Upcoming | Sprint 1
|  | As a volunteer I need to be informed about the nearest afflicted area, number of afflicted citizens needing rescue and the amount of needs. |  | Medium |  | Upcoming
|  | As a volunteer I need to Know where the gathering points for the volunteering & means of transportation. |  | Medium |  | Upcoming
|  | As a volunteer I need to be updated with the newly data. |  | High |  | Upcoming | Sprint 1
| Afflicted(المنكوبين) | As an afflicted I need to inform about my case (info e.g.: location, time, flood, home destructed, blackout, stuck, injuries). |  | High |  | Upcoming | Sprint 1
|  | As an afflicted I need to Know the nearest available shelters, food, hospitals, etc. |  | High |  | Upcoming | Sprint 1
|  | As an afflicted I need to Know how to get to the nearest gathering points. |  | Medium |  | Upcoming

## Sprint Backlog
User Story | Perspective | Task | Estimated Cost | Status | Comments | Responsible | GitHub Issue
Sprint (1) 16.03.2017 - 06.04.2017
As Gov. we need to detect places & times of historical rainstorms from concerned authorities. | Gov. |  |  | Inprogress
As Gov. we need to detect places of Swales (المخرات) from concerned authorities. | Gov. |  |  | Inprogress
As Gov. we need to identify the most vulnerable places to rainstorms from concerned authorities. | Gov. |  |  | Inprogress
As Gov. we need to identify the urban contexts around swales from concerned authorities. | Gov. |  |  | Inprogress
As Gov. we need to inform citizens about shelter places. | Gov. |  |  | Inprogress
As Gov. we need to warn citizens about any expected rainstorms. | Gov. |  |  | Inprogress
As Gov. we need to setup an evacuation plan in case of rainstorms. | Gov. |  |  | Inprogress
As a volunteer I want to be able to inform about incidences. | Volunteer |  |  | Inprogress
As a volunteer I need to Register myself to provide services and support. | Volunteer |  |  | Inprogress
As a volunteer I need to be informed about the nearest afflicted area, number of afflicted citizens needing rescue and the amount of needs. | Volunteer |  |  | Inprogress
As a volunteer I need to Know where the gathering points for the volunteering & means of transportation. | Volunteer |  |  | Inprogress
As a volunteer I need to be updated with the newly data. | Volunteer |  |  | Inprogress
As an afflicted I need to inform about my case (info e.g.: location, time, flood, home destructed, blackout, stuck, injuries). | afflicted |  |  | Inprogress
As an afflicted I need to Know the nearest available shelters, food, hospitals, etc. | afflicted |  |  | Inprogress
As an afflicted I need to Know how to get to the nearest gathering points. | afflicted |  |  | Inprogress